## Slide 1
FORTRA
Engineering Assessment &
Path Forward
Root causes behind the dev↔test loops, budget pressure, and UAT slippage — and how we fix them
Prepared by Liam Jeong · June 25, 2026
CONSTRUCTIVE · FORWARD-LOOKING

## Slide 2
WHY THIS DECK
Purpose & context
• This deck consolidates the team's findings into a small number of structural root causes — with concrete, checkable evidence — and a practical path forward.
• Framing: most of what is driving the loops is structural / process, not effort. The aim is to convert the team's hard work into a codebase we can change safely and ship on schedule.
• Recommendations are calibrated to the team we actually have — 2 RCA + 3–4 SF developers, no spare runway, limited Git familiarity — so they need little time and no new tooling skills.
WHAT THIS IS — AND ISN'T
A root-cause assessment to inform a decision, not a critique of any individual. Every figure is reproducible from the org and dossiers. Where evidence is suggestive rather than proven, it is labeled as such.
Fortra RLM — Engineering Assessment & Path Forward
2
Confidential — internal working material

## Slide 3
THE BIG PICTURE
Executive summary — four root causes
1
No shared source of truth
~97% of running Apex & ~99% of flows are not version-controlled; the live org is edited directly.
2
Quality gates aren't continuous
Org-wide Apex coverage ~43–45% vs the 75% Salesforce requires to deploy to production.
3
Overlapping automation
Per-line flow fan-out + a redundant subflow overflow governor (SOQL/CPU) limits on large orders.
4
Scope not pinned in discovery
Volume, pricing math & migration feasibility were discovered reactively in UAT.
Common thread: each gap turns an ordinary fix into a re-investigation — which is the mechanism behind the dev↔test loops.
Fortra RLM — Engineering Assessment & Path Forward
3
Confidential — internal working material

## Slide 4
BALANCE & CREDIT
What's working — and where the problems concentrate
WORKING WELL
• A large amount of functionality is built and running under real schedule pressure.
• Testing found no major issues in Sales Cloud, Experience Cloud, or Data Cloud.
• Core Lead → Opportunity → Quote → Order progression is familiar and functioning.
• The team's effort, long hours and commitment are real and recognized by leadership.
WHERE THE PROBLEMS CONCENTRATE
• Nearly all material issues sit on the Revenue Cloud Advanced (RCA) side — pricing, ordering, Workday integration.
• RCA is a newer, sharper-edged platform: governor limits, ExpressionSet pricing, RLM data locks, immature migration tooling.
• This narrows the problem: it is the RCA layer's engineering practices and scope definition that need attention, not the whole build.
Implication: fixes can be targeted, not wholesale.
Fortra RLM — Engineering Assessment & Path Forward
4
Confidential — internal working material

## Slide 5
ROOT CAUSE 1
No shared, version-controlled source of truth
THE PROBLEM
• The code that runs the org is effectively not in version control.
• Only a handful of classes/flows are in a repo; the bulk lives only in the live org.
• No shared team repository, no CI, no git-backed promotion path. The one repo is single-author (not shared team VCS).
• So collaboration happens by editing the live org directly — no diff, no review, no rollback.
• This is a process gap, not a people problem: without a repo + pipeline, even careful engineers clobber each other.
EVIDENCE (CHECKABLE)
› force-app (deployable package): 12 Apex classes, 3 flows, 0 triggers
› Live org: 404 classes, 245 flows, 10 triggers → ~97% of Apex / ~99% of flows untracked
› Live-org mirror is gitignored — zero history
› Documented fallout: a production gack (572633412-308158) from an in-place edit; a flow change that silently re-introduced a closed defect (fixed by reverting); a pricing formula that oscillates between sessions
IMPACT Every fix starts from "what is actually live right now" — the re-discovery tax that drives the dev↔test loops.
Fortra RLM — Engineering Assessment & Path Forward
5
Confidential — internal working material

## Slide 6
ROOT CAUSE 2
Quality gates aren't continuous
THE PROBLEM
• Test coverage is treated as an end-of-build task, not a per-ticket habit.
• Org-wide Apex coverage is well below the level Salesforce requires to deploy to production.
• Several in-scope pricing classes are at very low coverage (2–37%).
• This is a hard platform gate — not a preference: the prod deploy is rejected until it clears, regardless of business sign-off.
EVIDENCE (CHECKABLE)
› Org-wide Apex coverage ~43–45% vs the mandatory 75% production gate
› In-scope pricing classes measured at 2–37% (authoritative peer-review run)
› A same-day remediation pass moved overall coverage only 43% → 45%
› No CI config in the repo to catch this continuously
IMPACT A hidden cutover blocker: go-live is gated until coverage clears 75% — better surfaced now than at the deadline.
Fortra RLM — Engineering Assessment & Path Forward
6
Confidential — internal working material

## Slide 7
ROOT CAUSE 3
Overlapping automation & an overgrown pricing engine
THE PROBLEM
• Multiple automations do overlapping work on the same transaction; the pricing engine keeps growing in place.
• On large orders this overflows Salesforce governor limits (SOQL & Apex CPU).
• "Optimize existing flows and Apex code" — raised by the team — sits here.
• Accreted, duplicate automation consumes the shared governor budget and makes every change riskier.
EVIDENCE (CHECKABLE)
› 3 OrderItem flows fan out per line → 51 flow interviews on a 17-line order → "Too many SOQL queries: 101" (UAT)
› A redundant duplicate subflow was the single largest contributor (~40%) — doing work an active flow already did
› A high-quantity convert breached the Apex CPU limit (401 line clones, 1,293 flow interviews)
› Pricing procedure: 110 steps across ~14 in-place versions, 9 prehook/posthook classes (2 redundant pairs); 18 obsolete flows still in the org
IMPACT Large / high-value orders fail in UAT until automation is consolidated and SOQL is lifted out of loops.
Fortra RLM — Engineering Assessment & Path Forward
7
Confidential — internal working material

## Slide 8
ROOT CAUSE 4
Scope & solution design not pinned down in discovery
THE PROBLEM
• Volume, pricing math, validations and migration feasibility were discovered during build/UAT, not up front.
• Solution-design E2E flow is not fully articulated — e.g. lookup filters and field-level validations (team-raised).
• No non-functional / volume requirements were captured; the realistic order-line ceiling is still an open question to the PO.
• Core pricing rules remain open (multi-currency, margin-vs-discount math, new vs renewal maintenance).
• Each discovery becomes its own RCA → fix → retest loop.
EVIDENCE (CHECKABLE)
› Design docs contain essentially no volume/NFR requirements; order size assumed far lower than business volumes
› Two governor defects found reactively in UAT (SOQL on large orders; CPU on high-quantity converts)
› ~24 distinct pricing / Workday-integration tickets worked in a ~3-week window
› Migration: ProductConfigurationRule + ≥8 other RCA objects had no supported migration path — found one-by-one during cutover
IMPACT The long tail of reactively-discovered gaps is the budget story — each gap is a fresh loop.
Fortra RLM — Engineering Assessment & Path Forward
8
Confidential — internal working material

## Slide 9
CONNECTING THE DOTS
How these root causes produce the loops & the overrun
Scope gap
A requirement (volume, pricing rule, validation) wasn't pinned down
Surfaces in UAT
It fails during testing as a defect, not a known task
Edit live to fix
With no repo/review, the fix is made directly in the org
Clobber / regress
Another in-place edit re-breaks it or a closed defect returns
Re-investigate
Next engineer re-retrieves to learn "what's actually live"
↺ …and back to UAT — the same loop repeats, multiplied across ~24 tickets and every large order.
Note: the claim that this is the primary driver of the overrun is a reasonable inference from the pattern, not a measured share. The pattern itself — gap → UAT defect → live edit → regression → re-investigation — is well evidenced.
Fortra RLM — Engineering Assessment & Path Forward
9
Confidential — internal working material

## Slide 10
IF WE CHANGE NOTHING
Risks if unaddressed
Cutover blocked at the platform tier
43–45% coverage → Salesforce rejects the production deploy until a multi-day hardening pass, regardless of sign-off.
Silent regressions & lost work
No diff/rollback on ~97% of running code → in-place edits keep clobbering and re-introducing closed defects.
Live pricing outages with no recovery
In-place edits to the single active pricing procedure (no atomic rollback) keep producing gacks, each a fresh RCA.
Recurring governor failures on the biggest orders
Without captured volumes + bulkified automation, large/high-quantity orders keep hitting SOQL/CPU limits.
Unbounded UAT slippage & budget overrun
Each reactively-discovered gap remains its own RCA-fix-retest loop — the current pattern continues.
Bus-factor / knowledge risk
History sits with one person and others' work lives only in the live org — no safe handoff if a developer rolls off.
Fortra RLM — Engineering Assessment & Path Forward
10
Confidential — internal working material

## Slide 11
THE PATH FORWARD
Recommendations — calibrated to the team we have
PLANNING REALITY: 2 RCA + 3–4 SF developers · no spare runway · limited Git familiarity. Each item below needs little time and no new tooling skills.
DO THIS WEEK (near-zero cost)
• Name one "source-of-truth owner" who saves a dated daily org pull — gives history + rollback with NO Git for anyone else.
• Shared "who's editing what today" register so two people never touch the same flow / pricing procedure at once — stops the clobbering.
• Remove the one proven-redundant duplicate subflow (~40% SOQL win, already diagnosed) — fixes the large-order failure.
• Freeze new pricing-procedure steps without the owner's sign-off.
BEFORE CUTOVER (focused, time-boxed)
• Targeted coverage sprint on ONLY the classes that gate the prod deploy — reach 75% org-wide, not perfection everywhere.
• Use the deploy tooling you already have (Gearset / change sets) for a repeatable sandbox→prod push — no command-line Git.
• Lock the few highest-risk open requirements with the PO in short sessions (order-line ceiling; open pricing rules).
DEFER (needs runway / resourcing)
• Full pricing-procedure refactor.
• Team-wide Git + CI / pull-request workflow — adopt gradually, after cutover.
• Org-wide coverage beyond the deploy-gating set.
• Name these openly so they're a decision, not a silent gap.
PRINCIPLE Stabilize with the people and tools we already have. Treat Git/CI maturity as a post-cutover journey, not a prerequisite for shipping.
Fortra RLM — Engineering Assessment & Path Forward
11
Confidential — internal working material

## Slide 12
DECISION TO FRAME WITH JOHN
Strategic options for the RCA layer
A solution discussion is active with Salesforce, Coastal and Fortra. With today's team (2 RCA + 3–4 SF devs) and no spare runway, the realistic default is to stabilize; a rebuild would require new time and senior RCA capacity.
OPTION A — Stabilize in place
REALISTIC NOW
• Keep working functionality; fix process + the few high-impact technical issues.
• Git-less source-of-truth owner, targeted coverage, remove the redundant subflow, lock open scope.
• Achievable with the current team; lowest disruption to an imminent UAT.
• Trade-off: pricing engine stays large; deeper refactor deferred to a post-cutover backlog.
OPTION B — Re-platform the RCA layer
NEEDS RE-RESOURCING
• Rebuild pricing/order automation on a clean, source-controlled foundation.
• Requires additional senior RCA capacity + a reset timeline + budget — not feasible with today's team.
• Risk of discarding functionality that already works.
• Only consider if leadership funds a reset.
RECOMMENDED
Stabilize now (Option A). Revisit Option B only if leadership adds runway and senior RCA capacity.
Either way, the "do this week" steps come first — they cost almost nothing and de-risk both paths.
Fortra RLM — Engineering Assessment & Path Forward
12
Confidential — internal working material

## Slide 13
MAKE IT CONCRETE
Proposed immediate next steps
This week (no new skills/tools)
☐ Name the source-of-truth owner; start dated daily org snapshots.
☐ Stand up the "who's editing what" register.
☐ Remove the redundant duplicate subflow.
☐ Book the PO session on the order-line ceiling.
Before cutover (current team)
☐ Targeted coverage sprint on the deploy-gating classes only.
☐ Repeatable sandbox→prod deploy via Gearset / change sets.
☐ Lock the open pricing rules with the business.
Decision gate (leadership)
☐ Confirm stabilize vs. re-platform — tied to whether extra runway + senior RCA capacity is on the table.
☐ Re-baseline the UAT / cutover plan against the agreed path.
None of this diminishes the team's effort — it converts that effort into a codebase we can change safely and a cutover we can trust.
Fortra RLM — Engineering Assessment & Path Forward
13
Confidential — internal working material

## Slide 14
APPENDIX
Evidence base (reproducible)
Theme | Finding (checkable) | Why it matters
Source control | force-app tracks 12 classes / 3 flows / 0 triggers; live org has 404 / 245 / 10 | ~97% Apex, ~99% flows unmanaged; live mirror gitignored
Source control | Single-author repo; other devs absent from history | Collaboration via live-org edits → clobbering, regressions
Quality gates | Org-wide coverage ~43–45% vs 75% gate; pricing classes 2–37% | Prod deploy blocked at platform tier until closed
Automation | 3 OrderItem flows × 17 lines = 51 interviews → SOQL 101 (UAT) | Large-order completion fails; ~40% from a redundant subflow
Automation | Pricing procedure 110 steps / ~14 versions / 9 hook classes; 18 obsolete flows | Recurring locus of pricing regressions
Scope/discovery | ~0 volume/NFR reqs in design; order ceiling open to PO; ~24 pricing tickets/3 wks | Governor defects (SOQL/CPU) found reactively in UAT
Scope/discovery | ProductConfigurationRule + ≥8 RCA objects had no migration path | Found one-by-one during cutover; unplanned effort
Fortra RLM — Engineering Assessment & Path Forward
14
Confidential — internal working material

## Slide 15
APPENDIX
Accuracy guardrails (stay defensible)
• The repo has a remote, but it is a single-author personal account — describe it as "not shared team version control," not "local-only."
• The large-order SOQL failure is on a UAT-only validation stack — call it a "UAT completion blocker on the largest orders," not a production blocker.
• The duplicate subflow was the largest single contributor (~40%), not the sole cause — the failure was multi-cause.
• Order-volume figures floated in testing are not business-confirmed — the defensible point is that the realistic ceiling was never captured and is open with the PO.
• Coverage: cite the durable range (43–45% vs 75%); per-class snapshots move day-to-day.
• In-place pricing-procedure editing is a recurring anti-pattern to replace — not an endorsed standard; reference the practice, not individuals.
• "Primary driver of the overrun" is a reasonable inference from the pattern, not a measured share — lead with the pattern.
Fortra RLM — Engineering Assessment & Path Forward
15
Confidential — internal working material